## Migration Checklist
Recommended Migration Timeline
Migration Checklist | WEEK
TASK | 1 | 2 | 3 | 4: Launch Week | 5 | 6
Implement Tracking Tag and Test
Program and profile setup*
Create list of affiliates to migrate
Audit affiliates, consider removing non-active affiliats
Announcement to affiliates about migration
Migrate Top 10 revenue partners
Migrate Top 20 revenue partners
Migrate remaining revenue partners
Final reminder to affiliates
Program closure on previous network
*Things to consider when setting up your ShareASale program:
Complete account details
Set up commission details
Deposit setup
Program partner terms
Partner approval criteria
Affiliate communications
Creative uploads
Data feed uploads

## US Tracker
Migration Planner
We recommend pulling 6-12 month performance for your affiliates to help prioritize outreach
Publisher Name | URL | # of Sales | Revenue | Commission | Clicks | CPA Rate | CPA Rate Notes | Contact Name | Contact Email | Initial Contact Date | Response Date | Chase Date | Join Date | Notes
Cartera Commerce | http://www.cartera.com/ | 16985 | 1821896.909 | 243682.838 | 96348 | 10% | Up to 15% | Jeff | jeff.leczkowski@cartera.com | 2022-04-14 | 2022-04-15 |  | 2022-04-29